## About
#VALUE!
STAKEHOLDER MAPPING TEMPLATE (V1.0 Released September 2025)
About This Template:
This Stakeholder Mapping template was developed as part of the C2ES Strategic Communication Playbook. There are two parts to this resource - internal and external. Please review the instructions for both before completing them.
The What:
A stakeholder map is a visual representation of the key individuals, groups, or organizations that have an interest in or influence over a project, business, or initiative. It helps identify and categorize stakeholders based on their level of interest and power, making it easier to develop strategies for communication and engagement.
The Why:
This exercise will help you: - Understand stakeholder perspectives, influence, and potential impact on your efforts - Identify and manage key people who can influence the success of your efforts - Build strong relationships that foster trust, collaboration, and support - Avoid conflicts down the line and ultimately improve outcomes
The How:
A good stakeholder mapping plan identifies: -The stakeholders (who they are and what level of influence or interest they have in your effort) -Your objectives for engaging each stakeholder -The information the stakeholders require -Most effective methods and channels for communication -How often these communications should occur

## Internal Instructions
STAKEHOLDER MAPPING: INTERNAL STAKEHOLDERS
This exercise is designed to strengthen internal workflows. Follow the seven steps below, check the Sample tab for guidance, and complete your responses in the "Your Map" tab.
Step 1:
Identify your internal stakeholders
Who are the decision makers at your organization? Who needs to be consulted or informed of pending decisions? List the names of your peers (individuals or stakeholder groups) who have a role in communicating your efforts – whether it is to the consumers, media, investors, board, or others. Place each stakeholder on the grid according to their interest and influence over communicating your work. Doing this will help you clearly see who needs to be informed vs. who needs to be more engaged or involved. Then, insert the stakeholder name, title, department, and level in the appropriate columns in the "Your Map" tab. [Level 1 = Manage Closely (high influence, high interest), Level 2 = Keep Informed (high influence, low interest), Level 3 = Keep Satisfied (low influence, high interest), Level 4 = Regular Minimal Contact (low influence, low interest) *See sample chart below
#VALUE!
Step 2:
Clarify the Purpose
Now that you know where each stakeholder falls on the grid, define exactly what you want to achieve through communication with them. Ask yourself, "What's the goal here?" It could be anything from rallying support to requesting assistance with a particular communication effort (e.g. help drafting the annual report). Consider the typical nature of your engagement with each stakeholder or stakeholder group. Do you routinely collaborate with them on reporting? Do they help shape messaging or provide approvals? Capturing this context will help clarify both the immediate purpose and the broader relationship. Use the “Purpose” column in the "Your Map" tab to capture your answers.
Step 3:
Identify Stakeholder Needs or Preferences
Based on your knowledge of the stakeholder and insights gathered from your conversations, document their specific needs and preferences in the chart below. Consider factors such as their preferred communication style (e.g., concise bullet points vs. detailed reports), time zone differences, and optimal times for receiving information (e.g., at the start of the day, week, or another preferred schedule). Use this section to record any details that will help tailor your communication effectively. Also, consider any key deadlines or approvals that should be noted so they can be incorporated into timelines. Capture this information in the "Needs / Preferences" column.
Step 4:
Identify Stakeholder Key Issues
Identify the key issue(s) each stakeholder is concerned about, and whether there are any must-have requirements (i.e., if this issue is not addressed, then nothing else matters). Proactively identifying challenges or barriers that may arise when engaging with each stakeholder will enable you to tailor your communication and engagement approach accordingly. Use the "Key Issues" column to capture your answers.
Step 5:
Determine Communication Method
The methods you choose might be based on preferences, demographics, goals, or resources. Some methods to consider include: -Regular progress reports -Email or online chat rooms -Presentations -Weekly in-person meetings -Digital newsletters or team collaboration channels Capture your answers for both routine and urgent communications in the appropriate columns.
Step 6:
Share Your Method With Key Stakeholders & Adjust as Needed
To ensure alignment and minimize confusion, clearly communicate your chosen communication method with key stakeholders. Seek their feedback to confirm it meets their needs. Additionally, discuss the collaboration and communication process for both routine interactions and unexpected situations, such as emergencies or urgent requests.
Step 7:
Define RACI Roles
Now that you’ve mapped out your stakeholders and communication plans, assign a RACI role to each stakeholder to clarify their role in your communication process. RACI definitions: -Responsible (R): Who is doing the work or owning the task? -Accountable (A): Who is ultimately answerable and has the final decision or sign-off? -Consulted (C): Who needs to be consulted for input before a decision or action? -Informed (I): Who needs to be kept up to date on progress or decisions? Tip: One person can hold more than one role, but only one person should be Accountable for each task or decision.

## Sample - Internal Stakeholders
Internal Stakeholders
Stakeholder Name | Department | Title | Level | Purpose | Needs / Preferences | Key Issues | Communication Method (Routine) | Communication Method (Urgent) | RACI Role | Notes
e.g. John Smith | Communications | Senior Director | 1 – Manage Closely | Get approval for key messaging | Needs detailed context | Wants to ensure messaging is consistent through time, does not conflict with other communication products | Weekly Check-in Meetings | Phone Call | A (Accountable)
| Strategic Planning | Director | 1 – Manage Closely | Align sustainability strategy with overall corporate strategy | Prefers email summaries | Seeks alignment of climate and sustainability strategies with overall business goals and identify related opportunities | Monthly Progress Reports | Slack Message | R (Responsible)
| Operations | Director | 1 – Manage Closely | Support integration of sustainability into operations; Facilitate emissions data collection during operational processes | Prefers email summaries | Wants to ensure sustainability activities do not hinder efficient operations | Weekly Check-in Meetings | Phone Call | C (Consulted)
| Investors Relations | Director | 1 – Manage Closely | Support preparation of the annual report to deliver tailored messaging to investors | Prefers email summaries | Wants to provide investors with clear and rational information | Monthly Progress Reports | Phone Call | R (Responsible)
| Finance | Senior Director | 2 – Keep Informed | Integrate management of climate and financial risks; Link sustainability KPIs with financial performance | Prefers reports format sharing | Wants to ensure financial returns for growth and operations | Quarterly Progress Reports and Presentation | Slack Message | C (Consulted)
| Legal and Compliance | Senior Manager | 2 – Keep Informed | Comply with sustainability regulations | Needs detailed context | Wants to integrate the standards and regulations for cohesive compliance, avoiding fragmentation | Bi-weekly Email Update | Phone Call | C (Consulted)
| Corporate Affairs | Senior Director | 2 – Keep Informed | Engage in collective advocacy and communication with industry peers | Prefers email summaries | Wants to make sure the alignment of interest within the industry peers initiatives | Weekly Email Update | Slack Message | I (Informed)
| Risk Management | Director | 2 – Keep Informed | Assess climate risks and develop response measures | Needs detailed context | Wants to remove, mitigate, ignore, or convert risk according to the impact it may cause | Weekly Check-in Meetings | Slack Message | R (Responsible)
| Marketing | Manager | 3 – Keep Satisfied | Align messaging across platforms; Help publicize annual report and speaking opportunities | Prefers email summaries | Wants climate & sustainability plans to align with and generate value for customers | Weekly Email Update | Slack Message | I (Informed)
| Human Resource | Senior Director | 3 – Keep Satisfied | Develop employee awareness of sustainability; Manage workforce impacts from climate risks | Prefers timely information sharing | Wants to avoid employee complaints from added workload and ensure cooperation | Monthly Email Update | Slack Message | A (Accountable)
| Supplier/Vendor Management | Senior Manager | 3 – Keep Satisfied | Conduct due diligence to ensure supplier compliance with sustainability standards and climate risk adaptation; Support Scope 3 data collection; Enable supplier diversification or provide support to enhance climate resilience. | Prefers email summaries | Wants to ensure suppliers and vendors can keep pace and not fall behind | Monthly Check-in Meetings | Phone Call | A (Accountable)
| IT/ Data | Senior Manager | 4 – Regular Minimal Contact | Ensure internal data security; Support management of sustainability-related data | Prefers showcasing through data | Wants to make data integration across the corporation | Monthly Email Update with raw data | Phone Call | C (Consulted)
Legend: Level | Legend: RACI
1 – Manage Closely | R (Responsible)
2 – Keep Informed | A (Accountable)
3 – Keep Satisfied | C (Consulted)
4 – Regular Minimal Contact | I (Informed)
Other (Please specify in the Notes)

## Your Map -Internal Stakeholders
Internal Stakeholders
Stakeholder Name | Department | Title | Level | Purpose | Needs / Preferences | Key Issues | Communication Method (Routine) | Communication Method (Urgent) | RACI Role | Notes
Communications
| Strategic Planning | [7 empty] | R (Responsible)
| Operations |  | 1 – Manage Closely
Investors Relations
Finance
Legal and Compliance
Corporate Affairs
Risk Management
Marketing
Human Resource
Supplier/Vendor Management
IT/ Data
Legend: Level | Legend: RACI
1 – Manage Closely | R (Responsible)
2 – Keep Informed | A (Accountable)
3 – Keep Satisfied | C (Consulted)
4 – Regular Minimal Contact | I (Informed)
Other (Please specify in the Notes)

## External Instructions
STAKEHOLDER MAPPING: EXTERNAL STAKEHOLDERS
When communicating about your climate, environmental, and social efforts, the target audience typically includes investors, customers, employees, community members, regulators, and industry peers. Each group has different concerns and expectations, so tailoring communication to each specific audience is crucial. Who do we need to reach and why? What issues resonate with them? What factors (e.g., cultural, political) influence them? What’s the most effective way to engage them? What data, stories, or metrics will be important to include when engaging with them? This exercise will help shape your Communication Plan. You will first identify your target audiences, then determine the appropriate messages and communication methods.
Step 1:
Identify your internal stakeholders
Who are the decision makers at your organization? Who needs to be consulted or informed of pending decisions? List the names of your peers (individuals or stakeholder groups) who have a role in communicating your efforts – whether it is to the consumers, media, investors, board, or others. Place each stakeholder on the grid according to their interest and influence over communicating your work. Doing this will help you clearly see who needs to be informed vs. who needs to be more engaged or involved. Then, insert the stakeholder name, title, department, and level in the appropriate columns in the "Your Map" tab. [Level 1 = Manage Closely (high influence, high interest), Level 2 = Keep Informed (high influence, low interest), Level 3 = Keep Satisfied (low influence, high interest), Level 4 = Regular Minimal Contact (low influence, low interest) *See sample chart below
#VALUE!
Step 2:
Clarify the Purpose
Now that you know where each stakeholder falls on the grid, define exactly what you want to achieve through communication with them. Ask yourself, "What's the goal here?" It could be anything from informing them about key updates or milestones to ensuring compliance with key regulations or requirements. More focused statements help to make sure your messages hit the mark. Be clear about what information you need to provide and what feedback would be useful to obtain. Use the “Purpose” column in the "Your Map" tab to capture your answers.
Step 3:
Identify Stakeholder Needs or Preferences
Based on your knowledge of the stakeholder and insights gathered from previous interactions or conversations, document their specific needs and preferences in the chart below. For example, when communicating with investors, you will want to focus on data-driven reporting, financial impact, and risk management. Or, when communicating with consumers, you may want to focus on community impact. Use the "Needs / Preferences" column to record any details that will help tailor your communication effectively.
Step 4:
Identify Possible Metrics or Materials
Now that you have identified your target audience, their priorities, and any preferences, consider the metrics or materials that will strengthen your communications. For example, if a stakeholder prioritizes job creation, what data points will effectively illustrate that impact? If you are engaging with consumers who value community, what stories or testimonials should be captured to bring the impact to life? Planning for these elements now is crucial, as retroactively collecting data or information can be challenging. Use the "Metrics / Materials" column to capture your answers.

## Sample - External Stakeholders
External Stakeholders
Stakeholder / Stakeholder Group | Level | Purpose | Needs / Preferences | Metrics / Materials | Notes
e.g. Institutional Investors | 1 – Manage Closely | Build investor confidence by showcasing performance and risk mitigation | Data-driven reporting, Financial impact, Climate risk disclosures | Annual report, Emissions reduction data, Climate risk scenario planning
e.g. Proxy Advisors | 1 – Manage Closely | Lead to positive recommendations and build investor confidence by showcasing performance and demonstrating risk mitigation | Data-driven reporting, Financial impact, Climate risk disclosures | Annual report, Emissions reduction data, Climate risk scenario planning
e.g. Consumers / Clients | 1 – Manage Closely | Maintain a positive brand image with consumers, ensuring consistency and trustworthiness of provision of product/service | Stable products/services supply unaffected by the climate crisis, Minimized product/service's environmental footprint | Sustainability impact stories, Understandable and accessible sustainability reports and articles
e.g. Board Members | 1 – Manage Closely | Provide high-quality data to enable the board to make informed decisions and effectively engage in sustainability-related decision-making | Data-driven reporting, Assessments of physical and transition climate risks, Financial impact | Climate risk scenarios and response measures, Company operations reports, Emissions reduction data
e.g. Local Community Members | 2 – Keep Informed | Build trust and demonstrate community value | Transparent and relatable storytelling, Visual content, Local job impact | Community impact stories, Testimonials, Local hiring stats
e.g. Media | 2 – Keep Informed | Spread performance and build positive brand image | Transparent information sharing, Sustainability storytelling | Emissions reduction data, Sustainability impact stories
e.g. Regulators | 2 – Keep Informed | Engage in regulatory development through advocacy and ensure timely compliance | Data-driven reporting, Transparent information | Sustainability performance data, Operational and financial performance data
e.g. Suppliers and Vendors | 3 – Keep Satisfied | Build stable and sustainable value chain | Strategies and implementation plans to address climate risks | Regulatory compliance strategy and roadmap
e.g. Employees | 3 – Keep Satisfied | Ensure retention/job security and motivation | Transparent disclosure of company information, Climate risk analysis and response measures regarding workforce | Climate risk reponse measures and ensurance metrics
e.g. NGOs, Guidance Frameworks, and Climate initiatives | 3 – Keep Satisfied | Engage in development and ensure timely alignment to build climate resilience and long-term corporate sustainability | Transparent data disclosure, Alignment with sustainable standards and frameworks | Emissions reduction data, Climate risk scenario planning
e.g. Banks | 3 – Keep Satisfied | Share risk management to enhance credibility and secure sustainability-linked loans | Data-driven reporting, Financial impact, Climate risk disclosures | Annual report, Emissions reduction data, Climate risk scenario planning, ESG disclosure
e.g. Industry Peers | 4 – Regular Minimal Contact | Collaborate to drive industry progress, advocate shared needs, and exchange best practices | Transparent status sharing, Productive dialogue, Joint initiatives | Initiative proposals and reports
e.g. Re/Insurers | 4 – Regular Minimal Contact | Management and addressing of ESG and climate risks | Transparent data disclosure, Financial impact, Climate risk disclosures | Climate risk scenario planning, ESG disclosure
Legend: Level
1 – Manage Closely
2 – Keep Informed
3 – Keep Satisfied
4 – Regular Minimal Contact
Other (Please specify in the Notes)

## Your Map -External Stakeholders
External Stakeholders
Stakeholder / Stakeholder Group | Level | Purpose | Needs / Preferences | Metrics / Materials | Notes
e.g. Institutional Investors
e.g. Proxy Advisors
e.g. Consumers / Clients
e.g. Board Members
Local Community Members
Media
Regulators
Suppliers and Vendors
Employees
NGO
Banks
Industry Peers
Re/Insurers
Legend: Level
1 – Manage Closely
2 – Keep Informed
3 – Keep Satisfied
4 – Regular Minimal Contact
Other (Please specify in the Notes)